#### RT6: Assessments of impacts of climate change

| Work Package number | 6.0 | Start date: | Month 1 |
| --- | --- | --- | --- |
| Activity type | RTD |  |  |
| Participant id (person-months): | UEA (1.5), UNILIV (0.5), SYKE (0.5), UNIVBRIS (0.5) |  |  |

Objectives Provide management and co-ordination of activities within RT6

Description of work WP6.0: Management of RT6 Task 6.0.1: An internal project web site will be set up in the first months of the project to facilitate interaction between RT6 partners. Task 6.0.2: Progress reports will be produced to the schedule set out by the Project Co-ordinator. Task 6.0.3: Side meetings will be held at the ENSEMBLES project meetings in order to discuss research and review progress towards the deliverables. Task 6.0.4: The participants of WP6.0 will form a management committee which will meet at intervals of 9-12 months, and will be in close e-mail contact throughout.

Deliverables D.6.0 Internal RT6 web site

Milestones and expected result

| Work Package number | 6.1 | Start date: | Month 1 |
| --- | --- | --- | --- |
| Activity type | RTD |  |  |
| Participant id (person-months): | UNIVBRIS (3.5), UREADMM (3), PIK (8), ULUND (0), METO-HC (4), CNRS-IPSL (0) |  |  |

Objectives To develop versions of the LPJ model , the Hadley Centre land surface exchange scheme (MOSES) and the IPSL global dynamic vegetation model (ORCHIDEE) to the point at which they can be used for the applications foreseen in WP6.1

Description of work WP6.1: Global changes in biophysical and biogeochemical processes – integrated analysis of impacts and feedbacks Task 6.1.1: To set up the input data Task 6.1.2: To perform model developments, principally with respect to (a) global implementation of managed forests, and (b) global implementation of crops. Task 6.1.3: To perform first set of offline model runs for the recent past, present and future.

Deliverables D6.1 Versions of the LPJ and Hadley Centre models which include interactive annual crops. Version of the LPJ mode with globally applicable representation of managed forests. Month 18

Milestones and expected result M6.1 Completion of preparation of most impact models Month 18

| Work Package number | 6.2 | Start date: | Month 1 |
| --- | --- | --- | --- |
| Activity type | RTD |  |  |
| Participant id (person-months): | UEA (5), SYKE (2.5), UREADMM (3), ULUND (0), UKOELN (3), NOA (3), DISAT (6), PAS (5), FMI (8), SMHI(2.5), UNIK (3), DIAS (3) |  |  |

Objectives To select, calibrate and test impact models and indices in preparation for guided climate change sensitivity analysis, construction of impact response surfaces and evaluation of the impacts of extremes. These models will operate within a probabilistic framework, incorporating where possible effects of adaptation and acclimatisation to climate change.

Description of work WP6.2: Linking impact models to probabilistic scenarios of climate change Task 6.2.1 Preparation of impact models for scenario analysis, Task 6.2.2 Collection of data for the calibration and testing of impact models and as reference data for model input. Task 6.2.3 Design of sensitivity analyses based on existing climate projections and some initial performance tests Task 6.2.4 Estimation of critical impacts thresholds for water resources based on historical drought and flood events Task 6.2.5 Development of models for understanding and evaluating the impacts of extremes. These models will operate within a probabilistic framework, incorporating where possible effects of adaptation and acclimatisation to climate change. Task 6.2.6 Analyses of arrival times of extremes based on long observed records. Task 6.2.7 Development of a GIS environment within which impacts models will be developed and analyzed.

Deliverables D6.2 first phase impact models to predict damage to human activities, the environment and tropical annual crops from climate extremes: e.g. wind storm, drought, flood and heat stress. Month 18 D6.3 calibrated and tested crop, hydrology and energy impact models, baseline data and scenarios for constructing preliminary impact response surfaces. Month 18

Milestones and expected result M6.2 Completion of data collection for calibration and testing of impact models and as reference data for model data. Delivery of data. Month 12 M6.3 Preliminary definitions of impact thresholds for development of probabilistic impacts assessments, taking into account responses to mean and extreme perturbations Month 18 M6.4 Completion of preparation of most impact models Month 18

| Work Package number | 6.3 | Start date: | Month 1 |
| --- | --- | --- | --- |
| Activity type | RTD |  |  |
| Participant id (person-months): | UNILIV (9), UREADMM (3), ARPA-SIM (24), JRC-IPSC (12), METEOSWISS (4), LSE (3), FAO (4), WINFORMATICS (9), IRI(3), EDF(2), DWD (2.5) |  |  |

Objectives Integration of seasonal-to-decadal application modelling within the ENSEMBLES EPS. Commencement of research and development for gaining maximising skill in the integrated modelling system.

Description of work ### WP6.3: Impact modelling at seasonal to decadal timescales. Task 6.3.1: Consultation on seasonal-to-decadal applications models requirements for downscaling and RCM integrations with partners in RT2B and WP3.6 Task 6.3.2: The integration of seasonal-to-decadal application models within a probabilistic ESM based on DEMETER hindcasts.

Deliverables D6.4: Seasonal-to-decadal application models running as part of an integrated probabilistic ESM based on DEMETER hindcasts Month 18

Milestones and expected result M6.5 Integration of seasonal-to-decadal application models within ESM using DEMETER and where available the pilot ENSEMBLES system Month 18