#### RT6: Assessments of impacts of climate change

| Work Package number | 6.1 | Start date: | Month 1 |
| --- | --- | --- | --- |
| Activity type | RTD |  |  |
| Participant id (person-months): | UNIVBRIS (3.5), UREADMM (3), PIK (8), ULUND (0), METO-HC (4), CNRS-IPSL (0) |  |  |

Objectives To develop versions of the LPJ model , the Hadley Centre land surface exchange scheme (MOSES) and the IPSL global dynamic vegetation model (ORCHIDEE) to the point at which they can be used for the applications foreseen in WP6.1

Description of work WP6.1: Global changes in biophysical and biogeochemical processes – integrated analysis of impacts and feedbacks Task 6.1.1: To set up the input data Task 6.1.2: To perform model developments, principally with respect to (a) global implementation of managed forests, and (b) global implementation of crops. Task 6.1.3: To perform first set of offline model runs for the recent past, present and future.

Deliverables D6.1 Versions of the LPJ and Hadley Centre models which include interactive annual crops. Version of the LPJ mode with globally applicable representation of managed forests. Month 18

Milestones and expected result M6.1 Completion of preparation of most impact models Month 18