#### RT6: Assessments of impacts of climate change

| Work Package number | 6.2 | Start date: | Month 1 |
| --- | --- | --- | --- |
| Activity type | RTD |  |  |
| Participant id (person-months): | UEA (5), SYKE (2.5), UREADMM (3), ULUND (0), UKOELN (3), NOA (3), DISAT (6), PAS (5), FMI (8), SMHI(2.5), UNIK (3), DIAS (3) |  |  |

Objectives To select, calibrate and test impact models and indices in preparation for guided climate change sensitivity analysis, construction of impact response surfaces and evaluation of the impacts of extremes. These models will operate within a probabilistic framework, incorporating where possible effects of adaptation and acclimatisation to climate change.

Description of work WP6.2: Linking impact models to probabilistic scenarios of climate change Task 6.2.1 Preparation of impact models for scenario analysis, Task 6.2.2 Collection of data for the calibration and testing of impact models and as reference data for model input. Task 6.2.3 Design of sensitivity analyses based on existing climate projections and some initial performance tests Task 6.2.4 Estimation of critical impacts thresholds for water resources based on historical drought and flood events Task 6.2.5 Development of models for understanding and evaluating the impacts of extremes. These models will operate within a probabilistic framework, incorporating where possible effects of adaptation and acclimatisation to climate change. Task 6.2.6 Analyses of arrival times of extremes based on long observed records. Task 6.2.7 Development of a GIS environment within which impacts models will be developed and analyzed.

Deliverables D6.2 first phase impact models to predict damage to human activities, the environment and tropical annual crops from climate extremes: e.g. wind storm, drought, flood and heat stress. Month 18 D6.3 calibrated and tested crop, hydrology and energy impact models, baseline data and scenarios for constructing preliminary impact response surfaces. Month 18

Milestones and expected result M6.2 Completion of data collection for calibration and testing of impact models and as reference data for model data. Delivery of data. Month 12 M6.3 Preliminary definitions of impact thresholds for development of probabilistic impacts assessments, taking into account responses to mean and extreme perturbations Month 18 M6.4 Completion of preparation of most impact models Month 18