#### RT6: Assessments of impacts of climate change

| Work Package number | 6.3 | Start date: | Month 1 |
| --- | --- | --- | --- |
| Activity type | RTD |  |  |
| Participant id (person-months): | UNILIV (9), UREADMM (3), ARPA-SIM (24), JRC-IPSC (12), METEOSWISS (4), LSE (3), FAO (4), WINFORMATICS (9), IRI(3), EDF(2), DWD (2.5) |  |  |

Objectives Integration of seasonal-to-decadal application modelling within the ENSEMBLES EPS. Commencement of research and development for gaining maximising skill in the integrated modelling system.

Description of work ### WP6.3: Impact modelling at seasonal to decadal timescales. Task 6.3.1: Consultation on seasonal-to-decadal applications models requirements for downscaling and RCM integrations with partners in RT2B and WP3.6 Task 6.3.2: The integration of seasonal-to-decadal application models within a probabilistic ESM based on DEMETER hindcasts.

Deliverables D6.4: Seasonal-to-decadal application models running as part of an integrated probabilistic ESM based on DEMETER hindcasts Month 18

Milestones and expected result M6.5 Integration of seasonal-to-decadal application models within ESM using DEMETER and where available the pilot ENSEMBLES system Month 18