#### RT5: Independent comprehensive evaluation of the ENSEMBLES simulation-prediction system against observations/analyses

| Work Package number | 5.0 | Start date: | Month 1 |
| --- | --- | --- | --- |
| Activity type | RTD |
| Participant id (person-months): | INGV (0), KNMI (0), ECMWF (0), UNILIV (0) |

Objectives Provide management and coordination of activities within RT5.

Description of work WP5.0: Management of RT5 The coordination will be done on a pro bono basis by INGV and KNMI through informal meetings and contacts between the WP coordinators. Since no specific funding for management is included in the RT, the organization of the workshop (Deliverable D5.1) and of the initial meeting will be done with the support of the Project Office. Task 5.0.1: An initial meeting of RT5 participants will be held early in the project to discuss the strategy for evaluating the ensemble prediction system. Task 5.0.2: RT5 will contribute to the ENSEMBLES website with information such as location of data, contact details, progress reports, summaries of meetings and key scientific developments etc. Task 5.0.3: Timely delivery of milestones, deliverables and progress reports and representation of RT5 at ENSEMBLES management meetings will be ensured. Task 5.0.4: Organization of a workshop on key issues and research priorities within RT5 for the period after the first 18 months.

Deliverables D5.0: Meeting report and RT reports (month 12, 18). D5.1: Workshop on RT5 key issues and research priorities for years 1.5-5 of ENSEMBLES (month 12)

Milestones and expected result

| Work Package number | 5.1 | Start date: | Month 1 |
| --- | --- | --- | --- |
| Activity type | RTD |
| Participant id (person-months): | KNMI (18), UEA (5), UOXFDC (3), METEOSWISS (14) |

Objectives Production of daily gridded datasets for surface climate variables (max/min temperature, precipitation and surface air pressure) covering Europe for the greater part with a resolution high enough to capture extreme weather events and with attached information on data uncertainty.

Description of work WP5.1: Development of daily high-resolution gridded observational datasets for Europe. Task 5.1.1: Collate digitised daily data series from a dense network of meteorological stations to facilitate the gridding. Task 5.1.2: Quality control and analyse the raw data to ensure that non-climatic changes do not affect the station series. Task 5.1.3: Develop, test and evaluate gridding methods that are optimal for the daily time resolution and the space resolution considered here.

Deliverables D5.8: Assessment of the available station density for the gridding and daily data quality/homogeneity (month 18). D5.9: Report on the analysis of possible gridding methods (month 18).

Milestones and expected result M5.4: Selection of "best-performing" interpolation scheme for producing the daily gridded datasets (month 18).

| Work Package number | 5.2 | Start date: | Month 1 |
| --- | --- | --- | --- |
| Activity type | RTD |
| Participant id (person-months): | INGV (9), CNRS-IPSL (9), MPIMET (0), DMI (0), UREADMM (0) |

Objectives Identification and documentation of systematic errors in model processes and assessment of model phenomena and key uncertainties in ESMs and RCMs.

Description of work WP5.2: Evaluation of processes and phenomena. Task 5.2.1: Preparation of the tools to analyse systematic errors, variability and teleconnections in the simulations and reanalysis.

Deliverables D5.5: Preliminary report on systematic errors in the ENSEMBLE models (month 18). D5.6: Outline assessment of decadal forecast quality in the IndoPacific sector from the initial ENSEMBLES forecasts (month 18).

Milestones and expected result M5.3: Early assessment of systematic errors in the ENSEMBLES models (month 18).

| Work Package number | 5.3 | Start date: | Month 1 |
| --- | --- | --- | --- |
| Activity type | RTD |
| Participant id (person-months): | ECMWF (3), METEOSWISS (1), UREADMM (0), CNRS-IPSL (6) |

Objectives Assessment of the actual and potential seasonal-to-decadal quality for the different elements of the multi-model ensemble prediction system using advanced methods to evaluate the different attributes of forecast quality (skill, resolution, reliability, etc.).

Description of work WP5.3: Assessment of forecast quality. Task 5.3.1: Prototype of the forecast verification system, with beta-testing. Task 5.3.2: Development of advanced methods for the formulation and assessment of multi-model ensemble seasonal-to-decadal forecast quality.

Deliverables D5.3: Scientific article/report and Matlab software on optimal statistical methods for combining multi-model forecasts to make probabilistic forecasts of rare extreme events (month 18). D5.4: Scientific article/report on the best methods for verifying probability forecasts of rare events (month 18). D5.7: Assessment of the skill of seasonal NAO and PNA using multi-model seasonal integrations from DEMETER (month 18).

Milestones and expected result M5.2: Prototype of an automatic system for forecast quality assessment of seasonal-to-decadal hindcasts (month 18).

| Work Package number | 5.4 | Start date: | Month 1 |
| --- | --- | --- | --- |
| Activity type | RTD |
| Participant id (person-months): | KNMI (0.5), UREADMM (0), FTS-STU (0), IWS-STU (0), ETH (3), UEA (0), NOA (0) |

Objectives Assessment of the amount of change in the occurrence of extremes in (gridded) observational and RCM data.

Description of work WP5.4: Evaluation of extreme events in observational and RCM data. Task 5.4.1: Evaluation of ERA40 precipitation extremes in the Alpine region and decadal-scale variations therein, and evaluation of early simulations with the ETH 20 km RCM. These evaluations require dataset development. A 35 yr gridded data set of daily precipitation based on more than 7000 station series from the Alpine countries is available. The present grid resolution is 25 km. Several gridded datasets will be produced at different spatial resolutions, ensuring that the effective resolution of validation datasets are compatible with the effective resolution of ERA40 and the RCM simulations. Task 5.4.2: Consultation with WP2B.3 about study regions in WP5.4. Task 5.4.3: Preliminary discussions with WP2B.1 and RT3 about RCM data.

Deliverables D5.2: Assessment of the decadal-scale variations of precipitation extremes in ERA40 by comparison to observations in the Alpine Region (month 18).

Milestones and expected result M5.1: Evaluation of ERA40 precipitation extremes in the Alpine region completed (month 18).

| Work Package number | 5.5 | Start date: | Month 1 |
| --- | --- | --- | --- |
| Activity type | RTD |
| Participant id (person-months): | UNILIV (2), WHO (3), UREADMM (9), ARPA-SIM (7), JRC-IPSC (2), METEOSWISS (1), LSE (2), FAO (1), IRI (1), WINFORMATICS (0), EDF (1), DWD (1) |

Objectives Evaluation of the impacts models driven by downscaled reanalysis, gridded and probabilistic hindcasts over seasonal-to-decadal scales through the use of application specific verification data sets.

Description of work WP5.5: Evaluation of seasonal-to-decadal scale impact-models forced with downscaled ERA-40, hindcasts and gridded observational datasets. Task 5.5.1: Seasonal application models will be tested with ERA-40 data and selected models with DEMETER forecasts to commence development of validation systems. Task 5.5.2: A workshop on the use of seasonal probabilistic forecasting for health applications will be organised.

Deliverables D5.10: Workshop report on Lessons learned from seasonal forecasting: health protection (month 18)

Milestones and expected result