- Minor updates

- 23rd September

- Changes in purple

- 17th September

- Changes in blue

- Estimated indicative person-months" for the
deliverable X.X "Contribution to a paper on the value of s2d data for
reinsurance application in Europe" now 7, not 8 months.

- 14th September

- Changes in blue

- Minor updates 28th August

- WP6.2 FMI D6.15 details

- This version is last updated 23rd August

- Please use bold blue for the first round of changes.

- E-mail updated versions of the document to your work package leader and Andy Morse please.

- Minor changes can be communicated by e-mail to your WP leader copied to Andy Morse – but please make the e-mail clear.

- Andy is in South Africa from 31st August and is back in the office 14th September.  I hope to have some e-mail contact some of the time.

- RT6 Draft planning for months 37-60 (1 Sep 2007 – 31 August 2009)

Provide a detailed Implementation Plan (DIP) for the next 24 months of the project (i.e. to the end of the project), using the format, tabulations etc. of the previous 18 months plan, as included within Annex I (the DoW) to the contract. Remember that the last 6 months in the previous DIP overlap with the first 6 months in this DIP!

## 8.5 Deliverables list

Continue the deliverable numbers on from the numbers given in the previous DIP, and remember to include the deliverables that we previously set from months 37-42 (using the same numbers as in the previous DIP)

| Del. No. | Deliverable name | WP no. | Lead participant | Estimated indicative person-months | Nature | Dissemi-nation level | Delivery date |
| --- | --- | --- | --- | --- | --- | --- | --- |
| 6.5 | Global benchmarking of historical runs of LPJ, JULES and Orchidee (offline) and the Hadley Centre and IPSL coupled models (online) against a variety of terrestrial data sets. | 6.1 | UNIVBRIS, assisted by METO-HC | ? | R | PP | TBD |
| 6.12 | Preliminary global risk analysis for climate change, derived by forcing the offline global impacts models with outputs from the RT2a Stream 1 ensemble. | 6.1 | PIK | ? | R | PP | 36 |
| 6.16 | Version of LPJ including mammalian herbivory. | 6.1 | UNIVBRIS | 12/5 | P | PP | 54 |
| 6.17 | Global risk analysis for the impacts of climate change on key ecosystem properties. | 6.1 | PIK | 8/4 | R | PP | 60 |
| 6.18 | Assessment of historical and projected future climate impacts simulated with fully coupled models | 6.1 | METO-HC | ? | R | PP | 60 |
| 6.13 and 2B.26 | Recommendations and guidance on methods for the construction of probabilistic regional climate projections and their application in impact modelling | 6.2 | SYKE (with UEA for 2B.26) | 10 |  |  | Month 48 |
| 6.14 | Joint WP 6.2 paper on the use of probabilistic climate projections in assessing the risk of impacts in Europe | 6.2 | SYKE | 15 |  |  | Month 54 |
| 6.15 | Assessing the uncertainty in projected changes in climate extremes and their impacts on the following sectors: health, forestry, flood risk, property damage, agriculture | 6.2 | UEA OMIT ??? | 0 | R | PP | Month 48 |
| 6.16 | Joint WP 6.2 paper: Impacts of projected changes in climate extremes over Europe to 2100: a review of key sectors | 6.2 | UEA | 21 | R | PU | Month 54 |
| 6.19/2B.28 | Report on the assessment of changes in regional weather and climate and their impacts in East Mediterranean | 2B.3 and 6.2 | NOA | 5 | R | PU | Month 46 |
| 6.20 | Contribution to a paper on the value of s2d data for reinsurance application in Europe | WP6.3 | MeteoSwiss (52) | 7 | Scientific Publication |  | M54 |
| 6.21 | Report on the forecast quality of seasonal predictions of malaria incidence in Botswana over the period 1982-2005. | WP6.3/WP5.3 | IRI with ECMWF |  | Public report |  | M60 |
| 6.22 | Report on the quality of seasonal predictions of wheat yield and irrigation needs in Northern Italy | WP6.3 | ARPA |  | Public Report |  | M60 |

- 8.6 Work package description (24 months period, month 37-60)

| Work package number | 6.0 |  | Start date or starting event: |  | M37 |
| --- | --- | --- | --- | --- | --- |
| Activity Type |  |  |  |  |  |
| Participant id |  | UNILIV, UNIVBRIS, SYKE |  |  |  |
| Funded/unfunded Person-months |  | e.g. 2/4 (meaning 2 funded and 4 unfunded, giving a total of 6) |  | UNILIV (0.0/1.0), UNIVBRIS (0.0/0.5), SYKE (0.0/0.5) |  |

Objectives Provide management and co-ordination of activities within RT6

Description of work WP6.0: Management of RT6 Tasks 6.02 to 6.04 continue from months 25 to 42 Task 6.0.2: Progress reports will be produced to the schedule set out by the Project Co-ordinator. Task 6.0.3: Side meetings will be held at the ENSEMBLES project meetings in order to discuss research and review progress towards the deliverables. Task 6.0.4: The participants of WP6.0 have formed a management committee which will meet at intervals of 9-12 months, and will be in close e-mail contact throughout. Task 6.0.5 Further development of the RT website will be undertaken and more comprehensive WP web sites will be produced

Deliverables

Milestones and expected result

- 8.6 Work package description (24 months period, month 37-60)

| Work package number | 6.1 |  | Start date or starting event: |  | Month 37 |
| --- | --- | --- | --- | --- | --- |
| Activity Type |  |  |  |  |  |
| Participant id |  | UNIVBRIS, UREADMM, PIK, ULUND, METO-HC, CNRS-IPSL |  |  |  |
| Funded/unfunded Person-months |  | e.g. 2/4 (meaning 2 funded and 4 unfunded, giving a total of 6) |  | UNIVBRIS (?/?), UREADMM (?/?), PIK (8/8), ULUND (?/?), METO-HC (?/?), CNRS-IPSL (?/?) |  |

Objectives 1. To provide versions of the LPJ model, the Hadley Centre land surface model (JULES) and the IPSL global dynamic vegetation model (Orchidee), incorporating key features of human influence on ecosystems, including agriculture, irrigation, grazing and fire. 2. To benchmark the models—both offline, and where relevant within their respective GCM frameworks—against large-scale observational data sets for the 20th century. 3. Building on the ecosystem modelling and benchmarking work, to use the RT2a ensemble of climate model projections to provide a global risk analysis for the potential effects of climate change on ecosystem properties during the 21st century.

Description of work Task 6.1.5: Evaluating online models (Hadley Centre, IPSL) against terrestrial observational data. The RT2a ensemble will include “historical” time series of GCM outputs, including runs of the Hadley Centre and IPSL climate models with interactive (online) land-surface components. These models will produce outputs directly related to ecosystem processes such as net primary production, net ecosystem CO2 exchange and runoff. These outputs will be compared (within and between models) against the offline simulation results, and against the set of historical benchmarks already used for the historical offline runs of Orchidee, JULES and LPJ. This analysis will allow assessment of the extent to which a fully coupled (land-ocean-atmosphere) modellling approach can approximate the observed characteristics of the global carbon and water cycles. Task 6.1.7 (remaining part): Initial fire model implementation in the IPSL model. The IPSL implementation of fire-vegetation interactions is currently being amended to include the SPITFIRE algorithm, developed originally for LPJ, into the Orchidee modelling framework. This work will include offline testing of the coupled vegetation-fire dynamics Task 6.1.8: Implementation of mammalian herbivory in the LPJ model. Building on practical scoping work by ULUND and theoretical work by UNIVBRIS, a further version of LPJ will be developed to include the interactions among vegetation, herbivory and fire (D6.xx). Task 6.1.9: Risk analysis for climate change. The LPJ model (LPJmL) will be driven by climate change inputs from the RT2a ensemble. The analysis will use the methodology first designed by UNIVBRIS, with new metrics developed by PIK (for D6.12 and in subsequent work), to provide a parsimonious depiction of the impacts of different degrees of climate change on key properties of ecosystems worldwide. The analysis will include representative results from JULES and Orchidee to allow assessment of model dependence (D6.yy).

Deliverables D6.5 Global benchmarking of historical runs of LPJ, JULES and Orchidee (off-line) and the Hadley Centre and IPSL coupled models (on-line) against a variety of terrestrial data sets (by month 36). Request to delay on the grounds that RT2a Stream 2 ensemble, required for online model benchmarking, is not yet available. See PAR (UNIVBRIS). D6.16 Version of LPJ including mammalian herbivory (by month 54). D6.17 Global risk analysis for the impacts of climate change on key ecosystem properties (by month 54). D6.18 Assessment of historical and projected future climate impacts simulated with fully coupled models (by month 60).

Milestones and expected result M6.7 Global evaluation of on-line and off-line vegetation models (Month 36). Delay consequent on delay to RT2a Stream 2 ensemble M6.10/MM6.1 Completion of setting up of input data from ENSEMBLES model experiments for impacts modelling (all WPs). Delivery of input data. (Month 36). Delay consequent on delay to RT2a Stream 2 ensemble M6.11/MM 6.2 Completion of impact model calibration and validation (Month 36). Delay consequent on delay to RT2a Stream 2 ensemble ##### MM 6.3. Completion of offline biophysical and biogeochemical modelling. Delivery of offline modelling results (Month 48). Delay to month 54 to allow completion of new LPJ version including mammalian herbivory (D6.16) ##### MM 6.5 Completion of preliminary biophysical and biogeochemical online modelling (WP6.1). Delivery of online modelling results (Month 60).

- 8.6 Work package description (24 months period, month 37-60)

| Work package number | 6.2 |  | Start date or starting event: | M37 |
| --- | --- | --- | --- | --- |
| Activity Type |  |  |  |  |
| Participant id |  | DJF (formerly DIAS), DISAT, FMI, FUB, NOA, PAS, SMHI, SYKE, UEA, ULUND, UNIK, [UREADMM] |  |  |
| Funded/unfunded Person-months |  | DJF(2.75/2.75), DISAT(?/?), FMI(3/3), FUB(3.75/0.5), NOA(6/0), PAS(5.8/0), SMHI(2.55/2.55), SYKE(4.5/3), UEA(2/1), ULUND(0/0), UNIK(6/0), UREADMM(0.0/0.0) |  |  |

Objectives To select, calibrate and test impact models for use in estimating future risks of climate change To undertake preliminary impact model sensitivity analysis and scenario runs to construct impact response surfaces and evaluate the impacts of extremes. To define critical thresholds of impacts for relevant sectors and regions and obtain preliminary estimates of the likelihood of exceeding these thresholds using probabilistic information about future climate

Description of work WP6.2: Linking impact models to probabilistic scenarios of climate change Task 6.2.1 Preparation of impact models for scenario analysis (DIAS, DISAT, FUB, SMHI, UREADMM) (Completed) Task 6.2.2 Collection of data for the calibration and testing of impact models and as reference data for model input (DISAT, FUB, ULUND, UREADMM) (Completed) Task 6.2.3 Design of sensitivity analyses based on existing climate projections and some initial performance tests (FUB, SYKE, ULUND, UNIK) (Completed) Task 6.2.4 Estimation of critical impacts thresholds for water resources based on historical drought and flood events (SMHI, UNIK) (Completed) Task 6.2.5 Development of models for understanding and evaluating the impacts of extremes. These models will operate within a probabilistic framework, incorporating where possible effects of adaptation and acclimatisation to climate change. (FUB, NOA, UEA, ULUND) (Ongoing) Task 6.2.6 Analyses of arrival times of extremes based on long observed records. (UEA) (Ongoing) Task 6.2.7 Development of a GIS environment within which impacts models will be developed and analyzed. (Completed) Task 6.2.8: Construction of impact response surfaces for selected impact models of crops, soil carbon and nitrogen, and water resources (DIAS, DISAT, SMHI, SYKE, UNIK) (Ongoing) Task 6.2.9: Preliminary scenario impacts and risk assessment from available climate projections for selected models of crops, runoff, permafrost, soils, (DISAT, FMI, SMHI, SYKE) (Completed) Task 6.2.10: Preliminary evaluation of the impacts of extreme events using selected impact models for crops, human health, forest fire, forest damage, intense precipitation, drought, wind and temperature extremes from available climate projections (DISAT, FMI, FUB, NOA, PAS, UEA, ULUND, UREADMM) (Ongoing) Task 6.2.11: Application of preliminary results from the Ensembles Prediction System to impact models for estimating risks of extremes and risks of impacts (SYKE and all partners) (Ongoing) New Task 6.2.12: Compilation and analysis of final results and drafting of joint paper on the application of probabilistic climate projections for assessing risks of impacts in Europe New Task 6.2.13: Compilation of final model results of the impacts of climate extremes, analysis of the uncertainties in estimates, and drafting of a joint paper on the impacts of projected changes in climate extremes on climate-sensitive sectors in Europe.

Deliverables We propose to add 4 new deliverables in month 4 (D2B.28, joint deliverable with RT2B), month 54 (D6.14) and month 54 (D.6.15). D6.13: Methodological report on the linking of preliminary probabilistic projections from the Ensemble Prediction System to impact models. Month 42 D6.14: Joint WP 6.2 paper on the use of probabilistic climate projections in assessing the risk of impacts in Europe. Month 54 D6.15 Assessing the uncertainty in projected changes in climate extremes and their impacts on the following sectors: health, forestry, flood risk, property damage, agriculture. Month 48 D6.16: Joint WP 6.2 paper: Impacts of projected changes in climate extremes over Europe to 2100: a review of key sectors. Month 54 D6.19 Report on the assessment of changes in regional weather and climate and their impacts in East Mediterranean. Month 46 with RT2B.3

Milestones and expected result We are still on schedule to achieve Milestone 6.14 and Major Milestone 6.4 (see DoW), but this progress is entirely contingent on the timely delivery of probabilistic projections from the ensemble climate forecasting system (RT2B). M6.14: Completion of preliminary probabilistic assessments of climate change impacts using calibrated impact models: Month 42 Major milestone 6.4 (original DoW): Completion of probabilistic assessments of climate change impacts, and impacts at seasonal to decadal timescales for the core activities: crops, water resources, forests, energy, insurance and human health. (WP6.2 and 6.3). Month 48

- 8.6 Work package description (24 months period, month 37-60)

| Work package number | 6.3 |  | Start date or starting event: |  | Month 37 |
| --- | --- | --- | --- | --- | --- |
| Activity Type |  |  |  |  |  |
| Participant id |  | e.g. 1 |  |  |  |
| Funded/unfunded Person-months |  | e.g. 2/4 (meaning 2 funded and 4 unfunded, giving a total of 6) |  | UNILIV(20/0), UREADMM (0/0), ARPA-SIM (4/4), JRC-IPSC (4.6/4.6), METEOSWISS (0/7), LSE (11/3), IRI (?/?), EDF (0/2), DWD (inactive) |  |

Objectives [the default is to use the same description as in the first DoW] Integration of seasonal-to-decadal application modelling within the ENSEMBLES EPS. Continued research and development for methods that lead to maximising skill in the integrated modelling system. This final period sees the consolidation of work that has been ongoing with tasks continuing to make us of the new ENSEMBLES model data as it becomes available.

Description of work [WP/RT coordinators to number new tasks following on from where the original DoW got to, and number continuing tasks the same as in the original DoW. I will try to check for inconsistencies. Remember to look at the Tasks you set for the full 5 years to check those tasks are being done] Task 6.3.3 Assessment of downscaling and bias correction methodologies for seasonal integrations – downscaling in conjunction with RT2B Task 6.3.4 Evaluation of ensemble weighting and/or other methodologies through the application of user models to increase integrated model skill (LSE to lead) Task 6.3.6 Seasonal weather risk community – Operational Seasonal and Climate Risk (OCSR) Workshop. Additional OCSR workshops planned for years 4-5, with significant interaction with users. (LSE) Task 6.3.7 (Development of Task 6.3.5) Use of pre-production seasonal to decadal data sets and production runs (when available) to allow integration of user application models in the ENSEMBLES integrations.

Deliverables D6.20: Scientific publication on the potential value of s2d data for the reinsurance sector, namely the European winter wind storm risk. (MeteoSwiss) M54 D6.21 Report on the forecast quality of seasonal predictions of malaria incidence in Botswana over the period 1982-2005. (IRI with WP5.3 ECMWF) M60 D6.22 Report on the quality of seasonal predictions of wheat yield and irrigation needs in Northern Italy (ARPA) M60

Milestones and expected result M6.9 Integration of seasonal-to-decadal application models using pre-production ENSEMBLES seasonal to decadal hindcast (originally M30 but delayed until after Prague) Major milestone 6.4 (original DoW): Completion of probabilistic assessments of climate change impacts, and impacts at seasonal to decadal timescales for the core activities: crops, water resources, forests, energy, insurance and human health. (WP6.2 and 6.3). Month 48 as this is similar to M6.9 we need to discuss this one in Prague as there are issues with data..

Please indicate the nature of the deliverable (R=report, P=prototype, D=demonstrator, O=other)

Please indicate the dissemination level (PU=public, PP=restricted to other programme participants including the Commission Services, RE=restricted to a group specified by the consortium including the Commission Services, CO=confidential, only for member of the consortium including the Commission Services

Month in which deliverables will be available. Month 1 marking the start of the project, and all delivery dates being relative to this start date.

For Integrated Projects each workpackage must relate to one (and only one) of the following four possible Activity Types:  RTD/Innovation activities, Demonstration activities, Training activities, Management  activities

Milestones are points where major results have successfully been achieved as the basis for the next phase of work, or are control points at which decisions are needed; for example concerning which of several technologies will be adopted as the basis for the next phase of the project.

For Integrated Projects each workpackage must relate to one (and only one) of the following four possible Activity Types:  RTD/Innovation activities, Demonstration activities, Training activities, Management  activities

Milestones are points where major results have successfully been achieved as the basis for the next phase of work, or are control points at which decisions are needed; for example concerning which of several technologies will be adopted as the basis for the next phase of the project.

For Integrated Projects each workpackage must relate to one (and only one) of the following four possible Activity Types:  RTD/Innovation activities, Demonstration activities, Training activities, Management  activities

Milestones are points where major results have successfully been achieved as the basis for the next phase of work, or are control points at which decisions are needed; for example concerning which of several technologies will be adopted as the basis for the next phase of the project.

For Integrated Projects each workpackage must relate to one (and only one) of the following four possible Activity Types:  RTD/Innovation activities, Demonstration activities, Training activities, Management  activities

Milestones are points where major results have successfully been achieved as the basis for the next phase of work, or are control points at which decisions are needed; for example concerning which of several technologies will be adopted as the basis for the next phase of the project.