- 23 Sept updates in purple

- Draft planning for months 37-60 (1 Sep 2007 – 31 August 2009)

Provide a detailed Implementation Plan (DIP) for the next 24 months of the project (i.e. to the end of the project), using the format, tabulations etc. of the previous 18 months plan, as included within Annex I (the DoW) to the contract. Remember that the last 6 months in the previous DIP overlap with the first 6 months in this DIP!

## 8.5 Deliverables list

Continue the deliverable numbers on from the numbers given in the previous DIP, and remember to include the deliverables that we previously set from months 37-42 (using the same numbers as in the previous DIP)

| Del. No. | Deliverable name | WP no. | Lead participant | Estimated indicative person-months | Nature | Dissemi-nation level | Delivery date |
| --- | --- | --- | --- | --- | --- | --- | --- |
| D5.x | Report on verification scores used by ENSEMBLES seasonal application groups. | 5.5 | UNILIV |  | Public report |  | M54 |
| D5.x | Report on the impact of downscaling on forecast skill | 5.5 | TBD |  | Public report |  | M58 |

- 8.6 Work package description (24 months period, month 37-60)

| Work package number |  |  | Start date or starting event: |  |  |
| --- | --- | --- | --- | --- | --- |
| Activity Type |  |  |  |  |  |
| Participant id |  | e.g. 1 |  |  |  |
| Funded/unfunded Person-months |  | e.g. 2/4 (meaning 2 funded and 4 unfunded, giving a total of 6) |  | UNILIV(10.5/0), UREADMM (0/0), ARPA-SIM (2/2), JRC-IPSC (3/3), METEOSWISS (0/0), LSE (1/2), IRI (?/?), EDF (0/2), DWD (inactive) |  |

Objectives [the default is to use the same description as in the first DoW] The overall objective is the evaluation of the impacts models driven by downscaled reanalysis, other gridded data sets and probabilistic hindcasts over seasonal-to-decadal scales through the use of application specific verification data sets and reference forecasts

Description of work [WP/RT coordinators to number new tasks following on from where the original DoW got to, and number continuing tasks the same as in the original DoW. I will try to check for inconsistencies. Remember to look at the Tasks you set for the full 5 years to check those tasks are being done] The tasks are not partner specific and a number of partners will contribute to each task. Task 5.5.3 (updated and modified) Seasonal application models will be run with reference forecasts e.g. ERA-40 reanalysis and downscaled reanalysis data for comparison and assessment of skill gain. The same procedure will be undertaken with ENSEMBLES (as they become available) and DEMETER integrations for comparison of the impact of downscaling on forecast skill at both Tier-2 and Tier-3 levels Task 5.5.4 (updated and modified) Seasonal EPS application models will be run with DEMETER and ENSEMBLES hindcasts (as they become available) to be Tier-2 validated against reference forecast runs (e.g. ERA-40) and be to Tier-3 validated against real world observations (where available). This task will provide interaction with WP5.3. Task 5.5.5 An introductory tutorial on the use of well calibrated (perfect) probabilistic forecasts in the health field. Tutorial materials to be made available to ENSEMBES team (LSE) Task 5.5.6 Collation of user validation data, where available, for us in Toer-3 validations.

Deliverables D5.x Report on verification scores used by ENSEMBLES seasonal application groups. (UNILIV) M54 D5.x Report on the impact of downscaling on forecast skill. M58 (TBD)

Milestones and expected result M5.X Report on skill of ENSEMBLES forecasts from application perceptive (M58) (UNILIV)

Please indicate the nature of the deliverable (R=report, P=prototype, D=demonstrator, O=other)

Please indicate the dissemination level (PU=public, PP=restricted to other programme participants including the Commission Services, RE=restricted to a group specified by the consortium including the Commission Services, CO=confidential, only for member of the consortium including the Commission Services

Month in which deliverables will be available. Month 1 marking the start of the project, and all delivery dates being relative to this start date.

For Integrated Projects each workpackage must relate to one (and only one) of the following four possible Activity Types:  RTD/Innovation activities, Demonstration activities, Training activities, Management  activities

Milestones are points where major results have successfully been achieved as the basis for the next phase of work, or are control points at which decisions are needed; for example concerning which of several technologies will be adopted as the basis for the next phase of the project.