# WP5.5 draft Aug4 please quote in all updates

# RT5 ENSEMBLES Periodic Activity Report – 1Sep04-31Aug05

# Overview of activities carried out during the reporting period

## 1. Research Theme objectives and major achievements during the reporting period

This is an Executive summary, perhaps ~1 page

- Give an overview of RT objectives, show the RT’s current relation to the state-of-the-art

The main objective of WP5.5 is to examine the skill of application and impacts models when forced with seasonal scale ensemble prediction forecasts.  This is undertaken by running downscaled or local reference data as the ideal forecasts and making comparisons, using community employed verification techniques with, seasonal downscaled and post processed (e.g. partial bias correction) probabilistic ensemble hindcasts.

Initial work will be with existing data sets e.g. ERA-40 and the DEMETER ensemble prediction system (EPS) hindcasts.

- At the start of the project only limited data runs and verification of application model output had been undertaken.  The runs were with seasonal EPS, mostly FP5 DEMETER, and access to downscaled EPS output was limited.

- Summarise the objectives for the reporting period, work performed, contractors involved and the main achievements in the period

- Most partners’ activity will start up through the next 18 month period (M13 to M30) as data output from initial integrated modelling system runs will start to be validated.  Some partners have started work on systems for the initial validation of application model output (UNILIV, IRI)

- If applicable, comment on the most important problems during the period including the corrective actions undertaken. And clarify the changes and impact on planned milestones, if any

- Three partners withdrew or did not start the project no major long term impact of these withdrawals is anticipated and a specific deliverable for M18 directly involving one of these partners is anticipated to be delivered on time

- Provide e brief description of the expected end results from the RT, and a brief description of the intentions for use of the RT’s output, and the impact of the RT’s output

- Provide short comments and information on co-ordination activities, such as communication between partners, project meetings, possible co-operation with other project/programmes etc.

## 2. Research Theme progress of the period

For each Research Theme, present information under the following headings:

## a) Research Theme objectives and starting point of work at beginning of reporting period

Workpackage WP5.5 will examine the skill-in-hand for seasonal scale forecasts by running a number of impact models; firstly, with appropriately downscaled ERA-40 data and gridded datasets developed in WP5.1, and secondly, with downscaled and post processed (e.g. partially bias corrected) probabilistic ensemble hindcasts at seasonal-to-decadal scales from WP6.3. The models and applications include agriculture models (crop yield models for Europe and the tropics, agri-environmental impact models), infectious tropical diseases and energy demand.

This work package runs directly linked to WP6.3, where the seasonal ensemble forecast application model integrations are produced. WP5.5 covers the quality of the input data from the seasonal hindcasts, reanalysis and gridded data sets; and the validation of the impacts models when run with original and downscaled data and before and after post processed (e.g. partial bias correction) probabilistic hindcasts.  As methods to improve model skill are developed in 6.3 they will be validated in 5.5.

- Initial work will be with existing data sets e.g. ERA-40 and the DEMETER ensemble prediction system (EPS) hindcasts.

- At the start of the project only limited data runs and verification of application model output when run with seasonal EPS mostly with FP5 DEMETER and access to downscaled EPS output was limited.

## b) Progress towards objectives – tasks worked on and achievements made with reference to planned objectives, identify contractors involved

Task 5.5.1: Seasonal application models will be tested with ERA-40 data and selected models with DEMETER forecasts to commence development of validation systems.

The majority of groups have started running their models both with reference data (ERA-40) and DEMETER hindcasts as part of their WP 6.3 activity.  Most partners will commence development of validation systems during M12 to 18 – links have been made with RT5 to try and standardise the use of techniques utilising project standard code and algorithms.  Some partners have started to work on validation of application model output either through developing validation systems (UNILIV) or comparison of statistical model results with real world data (IRI)

Initial work on appropriate skill scores for application groups has been undertaken (LSE)

MeteoSwiss were not active through this reporting period.

Task 5.5.2: A workshop on the use of seasonal probabilistic forecasting for health applications will be organised.

The workshop is in advanced stages of preparation, although withdrawn from the project, WHO has continued to have an input to this task greatly supported by IRI with input from other partners (UNILIV and UNIFR from RT8).  A number of WP6.3 partners will be making presentations at the workshop they are LSE, IRI and UNILIV.  The workshop will be part of a wider Climate, Climate Change and Human Health workshop in Wengen, Switzerland, 12th to 14th September taking place on of day one of the meeting.

## c) Deviations from the project work programme, and corrective actions taken/suggested: identify the nature and the reason for the problem, identify contractors involved

- There have been no deviations from the work plan. However, it should be noted that three partners withdrew or did not start the project - two (WHO and FAO) due to contracture reasons and one (WINFORMATICS) for commercial reasons.  No major long term impact of these withdrawals is anticipated apart form reducing the scope of application under study.    WINFORMATICS had no funding or scheduled activity in the first 18 months, FAO were due to receive a small amount of funding and WHO were to work towards a M18 deliverable.  The M18 deliverable is still on target and WHO have continued to work unfunded and substantial input has been made by IRI and with supporting input from UNILIV and UNIFR from RT8.

## d) List of deliverables, including due date and actual/foreseen submission date (see Table 1)

No deliverables this reporting period

Table 1: Deliverables List

List all deliverables, giving date of submission and any proposed revision to plans.

| Del. no. | Deliverable name | Research Theme no. | Date due | Actual/Forecast delivery date | Estimated indicative person-months *) | Used indicative person-months *) | Lead contractor |
| --- | --- | --- | --- | --- | --- | --- | --- |

*) if available

## e) List of milestones, including due date and actual/foreseen achievement date (see Table 2)

No milestones this reporting period

Table 2: Milestones List

List all milestones, giving date of achievement and any proposed revision to plans.

| Milestone no. | Milestone name | Research Theme no. | Date due | Actual/Forecast delivery date | Lead contractor |
| --- | --- | --- | --- | --- | --- |

## Appendix 1 – Plan for using and disseminating the knowledge

In the plan for using and disseminating the knowledge the contractors will set out in a detailed and verifiable manner, the terms of use and dissemination of the knowledge arising from the project, which they own, in accordance with their interests (Article II.34.1 of the contract). It is an evolving document which should be updated annually to give a cumulative overview of the project’s undertaken and planned activities, and submitted at the end of each reporting period.

The final plan for using and disseminating the knowledge, as required at the end of the project, will therefore provide a complete picture of all activities undertaken and most importantly will provide information on the future route to full use (exploitation or use in further research) and dissemination of the knowledge.

The document should include the following three sections (Contractors concerned are only expected to fill in sections which are RELEVANT to the project):

Section 1 - Exploitable knowledge and its Use

This section will only present exploitable results, defined as knowledge having a potential for industrial or commercial application in research activities or for developing, creating or marketing a product or process or for creating or providing a service.

It should provide an overview, per exploitable result, of how the knowledge could be exploited or used in further research (if relevant). This should be created by the project coordinator obtaining input from each contractor that owns the knowledge and has an active role in its exploitation.

Both past and planned future activities should be included.

Where applicable please also include an explanation of why planned activities mentioned in previous reports have been discontinued or altered.

Overview table

| Exploitable Knowledge (description) | Exploitable product(s) or measure(s) | Sector(s) of application | Timetable for commercial use | Patents or other IPR protection | Owner & Other Partner(s) involved |
| --- | --- | --- | --- | --- | --- |
| 1. New superconductive Nb-Ti alloy | MRI equipment | 1. Medical 2. Industrial inspection | 2008 2007 | A materials patent is planned for 2006 | Partic. X (owner) Partic. Y, Partic. Z, Poss. licensing to equipment manuf. xyz |

The overview table should be accompanied by a short text per exploitable result, addressing the following issues (only when relevant):

- What the exploitable result is (functionality, purpose, innovation etc.);

- Partner(s) involved in the exploitation, role and activities

- How the result might be exploited (products, processes) - directly (spin offs etc) or indirectly (licensing) – on an individual basis or as a consortium/group of partners;

  - any technical and economic market considerations – commercial and technical thresholds etc.

  - any obstacles identified which might prove to be barriers to commercialization

    - the existence or development of similar or competing technologies / solution elsewhere

    - third party rights (eg patents belonging to competitors), standards,…

    - analysis of any (potential) non-technical obstacles

  - any form of non-commercial use or impact, relating e.g. to the development of new standards or policies

- Further additional research and development work, including need for further collaboration and who they may be;

- Intellectual Property Rights protection measures (patents, design rights, database rights, plant varieties, etc – include references and details);

- Any commercial contacts already taken, demonstrations given to potential licensees and/or investors and any comments received (market requirements, potential etc.);

- Where possible, also include any other potential impact from the exploitation of the result (socio-economic impact).

Section 2 – Dissemination of knowledge

The dissemination activities section should include past and future activities and will normally be in the form of a table maintained by the coordinator or any other person charged with controlling the dissemination activities.

Overview table

| Planned/actual Dates | Type | Type of audience | Countries addressed | Size of audience | Partner responsible /involved |
| --- | --- | --- | --- | --- | --- |
|  | Press release(press/radio/TV) | General public |  |  |  |
|  | Media briefing | Higher education |  |  |  |
|  | Conference | Research |  |  |  |
|  | Exhibition | Industry ( sector x) |  |  |  |
|  | Publications |  |  |  |  |
|  | Project web-site |  |  |  |  |
|  | Posters |  |  |  |  |
|  | Flyers |  |  |  |  |
|  | Direct e-mailing |  |  |  |  |
|  | Film/video |  |  |  |  |
|  | Please fill in any 5.5 outputs |  |  |  |  |

The overview table should be accompanied by a short description for each major activity (conference, exhibition, etc.) having taken place or planned since the last report.

Relevant details, such as references of journal publications and conferences, website addresses, dates, quantitative data, etc. should be explicitly mentioned.

Completed as well as future activities should be mentioned with their actual or planned date.

Useful guidance on how to disseminate the knowledge generated under the project can be found in the Commission publication entitled A guide to successful communications.

Section 3 - Publishable results

This section provides a publishable summary of each exploitable result the project has generated, and should therefore be included only when the consortium is ready to publicise and have taken the appropriate measures to protect their IPR.

For each exploitable result, this section should indicate:

- Result description (product(s) envisaged, functional description, main advantages, innovations)

- Possible market applications (sectors, type of use ..) or how they might be used in further research (including expected timings)

- Stage of development (laboratory prototype, demonstrator, industrial product...)

- Collaboration sought or offered (manufacturing agreement, financial support or investment, information exchange, training, consultancy, other)

- Collaborator details (type of partner sought and task to be performed)

- Intellectual property rights granted or published

- Contact details

These data will be entered in the CORDIS Results database which is open to the public and may be used by the Commission in its own promotional material. CORDIS will provide a template to collect the data and ensure that the required fields are filled (see http://www.cordis.lu/marketplace/about.htm#summ).

By the end of the project, this section of the final Plan for using and disseminating the knowledge will include a complete set of all publishable exploitable knowledge.

Anything to include here?

Knowledge: means the results, including information, whether or not they can be protected, arising from the project governed by this contract, as well as copyrights or rights pertaining to such results following applications for, or the issue of patents, designs, plant varieties, supplementary protection certificates or similar forms of protection (Article II.1.14 of the contract)

If exceptionally a contractor does not wish to disclose the text to the other contractors due to its commercial sensitivity, then they are asked to send the information directly to the Project Officer.

http://europa.eu.int/comm/research/conferences/2004/cer2004/pdf/rtd_2004_guide_success_communication.pdf

Please beware that only information which is readily available in the public domain should be included as this might affect the owner’s right to seek protection (eg patent) the results.